# Onboarding Runbook — one hotel

Target: 8 hours first time, 5 hours by the third hotel. Every hour above that is margin taken directly out of the engagement — at a 2-hour monthly support load the margin is 60.9%, and onboarding is where it goes.

# Why the hours matter more than the fee

|  | Hours | Cost at ৳1,200/hr | Effect |
| --- | --- | --- | --- |
| Fee for the first month | — | ৳19,000 | — |
| Onboarding, first hotel | 14 | ৳16,800 | Gross margin ≈ 3% in month one |
| Onboarding, target | 8 | ৳9,600 | Gross margin ≈ 45% in month one |
| Onboarding, by hotel three | 5 | ৳6,000 | Gross margin ≈ 64% in month one |
| Steady state, after month 3 | 2/month | ৳2,400/month | 60.9% margin — the model's base case |

The first hotel is nearly break-even on labour. That is normal and it is why you onboard three, not thirty. The runbook exists to make hotel two cheaper than hotel one.

# The sequence

Run the steps in this order. The order is not arbitrary: each step either costs or saves hours depending on whether the one before it is finished.

| # | Step | Minutes | Tool / artefact | Why this order |
| --- | --- | --- | --- | --- |
| 1 | Sign the LOI and the measurement plan | 30 | 06-design-partner-loi.docx, 04-measurement-plan.docx | Never touch data before the counterfactual is agreed. Everything downstream depends on it |
| 2 | Collect exports (12 months + pilot) | 45 | the eight CSVs in measurement/README.md | Self-serve where possible; the owner's patience is a finite resource |
| 3 | Baseline capture | 20 | measurement baseline --hotel | Completes measurement plan §2 from data rather than memory; the owner corrects a table, not a blank form |
| 4 | Data audit | 20 | measurement audit --hotel | Find the broken conversion event now, not in week three. Exits non-zero on blockers |
| 5 | Access grants | 60 | see the table below | Start invites early — several need another human to accept |
| 6 | Fix what the audit found | 60–120 | — | The variable step. Budget more for the first hotel |
| 7 | Knowledge interview | 45 | Annex A | Recorded, 30–45 minutes. This is where agent output quality comes from |
| 8 | Sign the measurement plan with real numbers | 30 | baseline.json → plan §2/§3 | Sign with the property's own figures in front of them |
| 9 | Set ceilings and approvers | 20 | LOI §3, personnel records | Who may approve spend and posts, in writing, before anything runs |
| 10 | First report dry run | 45 | measurement report --hotel | Read it together. Two wording changes now save five emails later |

# Access grants — start these on day one

| Access | Who must do it | Typical wait | Common failure |
| --- | --- | --- | --- |
| GA4 property read + admin for conversions | Property's web person | Same day | Nobody knows who owns the GA4 property. Ask for the login list first |
| Search Console read | Property | Same day | Verified on an old domain, not the live one |
| Google Ads manager-account link | Property | 1–2 days | They share a password instead. Do not accept it — link the accounts |
| Google Business Profile manager access | Property owner | 1–3 days | Invite sits unaccepted. Chase it twice, then schedule a call to accept it together |
| Booking engine reporting export | Booking engine vendor | 1–5 days | They only offer PDF. Ask for CSV or a scheduled email export |
| PMS / channel manager month-end report | Front office manager | 1–3 days | Staff turnover: the person who knows the report has left |
| Ad account billing stays with the property | Property | — | Never take this on. See LOI §4 |

# Step 6 — the variable step, and where the hours hide

In practice this is the only step that overruns, and it is always one of these four. If the audit is clean, this step is near zero — which is the entire argument for running the audit.

| Symptom the audit reports | Actual cause | Fix | Typical time |
| --- | --- | --- | --- |
| Conversions and bookings do not correlate | Conversion event fires on the wrong page, or on a thank-you page that reloads | Re-point the event at the booking-confirmed step; de-duplicate | 60–90 min |
| Attribution coverage above 70% | Site-wide UTM, or the booking record defaults the flag to true | Scope the campaign parameter to actual campaign landings; default to false | 45 min |
| Attribution coverage below 10% with spend running | The campaign parameter is dropped between landing and booking | Persist the parameter on the session and write it to the booking record | 60–120 min |
| OTA room-nights disagree with the engine | Booking-date vs stay-date reporting, or cancellations landing in one system | Agree which source is authoritative for which metric, and print the difference in every report | 30 min |

# Annex A — knowledge interview guide (30–45 minutes, recorded)

This is the highest-leverage 45 minutes in the engagement. Everything the content and media agents produce is conditioned on what you capture here, and nothing here is obtainable from a website.

| # | Question | What you are actually listening for |
| --- | --- | --- |
| 1 | Who is your best guest, and describe the last one who booked direct. | The real segment, not the marketing one |
| 2 | What do guests get wrong about the property before they arrive? | Expectation gaps that content should close |
| 3 | What do you refuse to be? Name three hotels people compare you to and why you are not them. | Brand boundaries — the most useful thing for tone-of-voice work |
| 4 | What is selling right now, and what is not? | Offers worth promoting, and the ones to keep quiet |
| 5 | What can you discount without damaging the rate? What must never be discounted? | The guardrail that stops a cheap-volume win |
| 6 | Which dates do you always sell out, and which do you never fill? | Where the work is genuinely incremental |
| 7 | What do guests ask on the phone that the website should answer? | Content topics that convert |
| 8 | What has a previous agency or freelancer done that you did not like? | The objection you will otherwise hit in month two |
| 9 | Who besides you can approve a post, and who can approve spend? | The approval map, in writing, before anything runs |
| 10 | If this works, what will you see that tells you so? | Their success definition — align the primary metric to it, or at least explain the difference |

Write the answers into knowledge_doc rows with kind = 'brand_voice', 'persona', 'offer' or 'fact_sheet', and mark them active only after the property has approved them. Versioned knowledge beats re-asking in three months.

# Annex B — the hours log, and why you must keep it

Every onboarding and support session goes in onboarding/hours.csv. Summarise it with:

python3 -m measurement.cli hours --log onboarding/hours.csv

That command prints hours per hotel and hours per step, worst first — which is your automation backlog in priority order. Do not guess at what to automate next; the log tells you, and it is the difference between building the thing that saves hours and building the thing that is interesting.

# Annex C — the exit at the other end

| When | Do this |
| --- | --- |
| At kickoff | Confirm in writing who owns each account; the property does, always |
| Monthly | Reread the hours log. If support hours are climbing, fix delivery before selling |
| At 90 days | Deliver the verdict from the report, including a stop. Record it in the plan |
| On exit | Revoke manager access, pause campaigns, export data, hand over knowledge, confirm in writing |